## Sprint1
|  |  |  | Week #1 (7.5 hrs / week) |  |  |  |  | Week #2 (7.5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 10 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
|  |  |  | 2022-03-13 | 2022-03-14 | 2022-03-15 | 2022-03-16 | 2022-03-17 | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | Days
|  |  |  | 60 | 54 | 48 | 42 | 36 | 30 | 24 | 18 | 12 | 0 | Ideal Burndown | Ideal Burndown
|  |  | 60 | 60 | 53 | 48 | 44 | 36 | 36 | 29 | 25 | 17 | 4 | Remaining Hrs (Total) | Remaining Hrs (Total)
Design Discussions | Project requirement analysis | All | 5 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5
| System Design discussions | All | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4
| Frontend requirement analysis | Abhiteja, Sai Kiran | 7 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 7
| Backend requirement analysis | Santhosh, Sandhya | 6 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 2 | 6
| UML Diagrams | Abhiteja | 8 | 0 | 2 | 0 | 0 | 0 | 0 | 3 | 0 | 2 | 1 | 8
| DB Design discussion | Santhosh | 6 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 6
Background Research | Complete research about backend frameworks | Sandhya | 8 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 2 | 8
| Complete research about frontend frameworks | Abhiteja | 5 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2 | 0 | 0 | 5
| Complete research about possible database options | Sai Kiran | 6 | 0 | 0 | 0 | 2 | 0 | 0 | 2 | 0 | 2 | 0 | 6
Team: | Hours per Week:
Abhiteja | 7.5
Sai Kiran | 7.5
Santhosh | 7.5
Sandhya | 7.5
Total Available Hours During Sprint: | 60

## Sprint2
|  |  |  | Week #3 (5 hrs / week) |  |  |  |  | Week #4 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 20 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
|  |  |  | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | Days
|  |  |  | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 0 | Ideal Burndown
|  |  | 40 | 40 | 39 | 38 | 35 | 25 | 24 | 22 | 16 | 11 | 0 | Remaining Hrs (Total)
Frontend | Wireframes | Sai Kiran | 7 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 5 | 7
| Login page | Sai Kiran | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 3
| Signup page | Abhiteja | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 2 | 5
| Employee login page | Abhiteja | 5 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | 0 | 1 | 5
Backend | Database schema design | Sandhya | 5 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 0 | 1 | 5
| Integration with database | Santhosh | 5 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 1 | 5
| Customer Login controller and logic | Sandhya | 5 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 5
| Employee Login controller and logic | Santhosh | 5 | 0 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 2 | 0 | 5
Team: | Hours per Week:
Abhiteja | 5
Sai Kiran | 5
Santhosh | 5
Sandhya | 5
Total Available Hours During Sprint: | 40

## Sprint3
|  |  |  | Week #5 5 hrs / week) |  |  |  |  | Week #6 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 12 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
|  |  |  | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | Days
|  |  |  | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 0 | Ideal Burndown | Ideal Burndown
|  |  | 40 | 40 | 35 | 32 | 29 | 25 | 22 | 17 | 14 | 8 | 4 | Remaining Hrs (Total) | Remaining Hrs (Total)
Frontend | Employee signup page | Sai Kiran | 4 | 1 | 0 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 4
| Search page | Sai Kiran | 6 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 6
| Booking summary page | Abhiteja | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 3
| Routing for customer and employee accounts | Abhiteja | 7 | 0 | 2 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 7
Backend | Customer Signup controller and logic | Sandhya | 4 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 4
| Employee Login controller and logic | Sandhya | 6 | 0 | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | 6
| Hotel search API | Santhosh | 7 | 2 | 0 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 7
| Create hotel booking API implementation | Santhosh | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 3
Team: | Hours per Week:
Abhiteja | 5
Sai Kiran | 5
Santhosh | 5
Sandhya | 5
Total Available Hours During Sprint: | 40

## Sprint4
|  |  |  | Week #7 5 hrs / week) |  |  |  |  | Week #8 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 12 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
|  |  |  | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | Days
|  |  |  | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 0 | Ideal Burndown | Ideal Burndown
|  |  | 40 | 40 | 40 | 32.5 | 28.5 | 25.5 | 25.5 | 22.5 | 17.5 | 12.5 | 0 | Remaining Hrs (Total) | Remaining Hrs (Total)
Frontend | JWT frontend integration | Sai Kiran | 7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 4 | 7
| Adding local storage | Sai Kiran | 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3
| Hotel booking page | Abhiteja | 5 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 5
| Integrate dynamic pricing | Abhiteja | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 | 3 | 0 | 5
Backend | Update hotel booking API implementation | Sandhya | 4 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4
| Delete hotel booking API implementation | Sandhya | 6 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 3 | 6
| Dynamic pricing implementation | Santhosh | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5
| Customer rewards management | Santhosh | 7.5 | 0 | 0 | 4.5 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 7.5
Team: | Hours per Week:
Abhiteja | 5
Sai Kiran | 5
Santhosh | 5
Sandhya | 5
Total Available Hours During Sprint: | 40

## Sprint5
|  |  |  | Week #9 (5 hrs / week) |  |  |  |  | Week #10 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 12 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
|  |  |  | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | Days
|  |  |  | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | Ideal Burndown | Ideal Burndown
|  |  | 40 | 40 | 38 | 32 | 26 | 26 | 25 | 21 | 14 | 4 | 0 | Remaining Hrs (Total) | Remaining Hrs (Total)
Frontend | Making pages responsive | Sai Kiran | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 4 | 0 | 8
| Routing for hotel booking endpoints | Sai Kiran | 2 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 2
| Integration with backend | Abhiteja | 7 | 0 | 1 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 7
| State management | Abhiteja | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3
Backend | Get bookings API | Sandhya | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 5
| Create hotel API | Sandhya | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 2 | 2 | 0 | 0 | 5
| Get hotel API | Santhosh | 4 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 2 | 0 | 4
| Backend validations for customer signin and signup | Santhosh | 6 | 0 | 0 | 2 | 0 | 0 | 1 | 0 | 1 | 1 | 1 | 6
Team: | Hours per Week:
Abhiteja | 5
Sai Kiran | 5
Santhosh | 5
Sandhya | 5
Total Available Hours During Sprint: | 40

## Sprint6
|  |  |  | Week #11 (5 hrs / week) |  |  |  |  | Week #12 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 12 x 2) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10
|  |  |  | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-05-06 | 2022-05-07 | 2022-05-08 | 2022-05-09 | 2022-05-10 | 2022-05-11 | Days
|  |  |  | 40 | 36 | 32 | 28 | 24 | 20 | 16 | 12 | 8 | 4 | Ideal Burndown | Ideal Burndown
|  |  | 40 | 40 | 39 | 34 | 30 | 27 | 25 | 19 | 14 | 8 | 0 | Remaining Hrs (Total) | Remaining Hrs (Total)
Frontend | Bug fixes | Sai Kiran | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 1 | 1 | 2 | 2 | 8
| UI enhancements | Sai Kiran | 2 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
| Redemption of customer rewards | Abhiteja | 5 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 1 | 1 | 0 | 5
| Refactoring project | Abhiteja | 5 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 1 | 5
Backend | Backend validations for employee signin and signup | Santhosh | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 3
| Validations for hotel booking API | Sandhya | 5 | 0 | 0 | 0 | 1 | 0 | 0 | 3 | 0 | 1 | 0 | 5
| Dynamic pricing algorithm corrections | Sandhya | 5 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5
| Integration with frontend | Santhosh | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3
| Bug fixes | Santhosh | 4 | Week #12 (5 hrs / week) D6: 1; Week #12 (5 hrs / week) D8: 1; Week #12 (5 hrs / week) D10: 2 | 4
Team: | Hours per Week:
Abhiteja | 5
Sai Kiran | 5
Santhosh | 5
Sandhya | 5
Total Available Hours During Sprint: | 40

## Sprint 7
Week #11 (5 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 12 x 2) | D1 | D2 | D3 | D4 | D5
|  |  |  | 2022-05-11 | 2022-05-12 | 2022-05-13 | 2022-05-14 | 2022-05-15 | Days
|  |  |  | 20 | 16 | 12 | 8 | 4 | Ideal Burndown | Ideal Burndown
|  |  | 20 | 20 | 16 | 13 | 2 | 2 | Remaining Hrs (Total) | Remaining Hrs (Total)
Deployment | Deployment of database | Santhosh | 1 | 0 | 0 | 0 | 1 | 0 | 1
| Deployment of backend | Sandhya | 1 | 0 | 0 | 0 | 1 | 0 | 1
| Deployment of frontend | Abhiteja | 1 | 0 | 0 | 0 | 1 | 0 | 1
| Cloud Environment Setup | Sai Kiran | 5 | 2 | 2 | 1 | 0 | 0 | 5
Testing | Testing of Database | Abhiteja | 2 | 0 | 0 | 0 | 2 | 0 | 2
| Testing of backend | Sandhya | 2 | 0 | 0 | 0 | 2 | 0 | 2
| Testing of frontend | Sai Kiran | 2 | 0 | 0 | 0 | 2 | 0 | 2
| Testing of scenarios | Santhosh | 0 |  | 2 | 2 | 2 | 0
Team: | Hours per Week:
Abhiteja | 5
Sai Kiran | 5
Santhosh | 5
Sandhya | 5
Total Available Hours During Sprint: | 40